## Slide 1: Case Study: Obamacare Website Failed Launch 2013

## Slide 2: Disclaimer
The entities affected by the incident have not disclosed all details of the incident publicly and likely will not do so in the future. However, sufficient information is available online and within the community to infer the probable events during the incident.
While efforts have been made to ensure the accuracy of the information provided, the presenter assumes no responsibility for its accuracy or for the consequences of its use.

## Slide 3: Sources of Information
This case study is adapted from the Obamacare website failed launch in 2013, utilizing information from public sources and modified for educational purposes.
For further details, please refer to the additional resource provided in this presentation.

## Slide 4: Readme Information
Target audience: Undergraduate, Graduate.
Keywords: Project management, Project planning, Software engineering
Last updated: May 1, 2024

## Slide 5: Learning Objectives
Describe the failed launch of the Obamacare website in 2013
Explain the best practices in project management and project planning
Explain the lessons learned from the Obamacare website failed launch

## Slide 6: Obamacare website
HealthCare.gov is a key piece of the Affordable Care Act, the law often called Obamacare, passed by Congress in 2010.
HealthCare.gov is made up of two main components, the data hub and the marketplace.
The website experienced significant crashes on its launch day in 2013, leading to widespread criticism across the nation.
This case study focuses on effective project management and project planning, which play a pivotal role in ensuring robust cybersecurity measures.
Source: https://en.wikipedia.org/wiki/HealthCare.gov

## Slide 7: Obamacare Website Failure Analysis
Healthcare.gov is arguably the most public software failure of the decade.
The problems with the insurance-shopping website include outages, slow page loads and the inability of users to complete coverage applications. Some insurance providers say they have been receiving inaccurate application information from the website.
Source: https://en.wikipedia.org/wiki/HealthCare.gov

## Slide 8: Examples of performance issues
Loading the Healthcare.gov home page takes a very long time.
Performance issues across the website.
The registration page of the site exemplifies poor adherence to best practices in Web Performance Optimization.
  They loaded about 55 Individual JavaScripts files and 11 Individual CSS files!
Source: https://en.wikipedia.org/wiki/HealthCare.gov

## Slide 9: Governments fail to learn from mistakes
Other government project failures
  FBI Trilogy
    http://www.infoworld.com/article/2672020/application-development/anatomy-of-an-it-disaster--how-the-fbi-blew-it.html
  DoD DIMHRS
    http://www.stripes.com/opinion/military-update-dimhrs-program-dumped-as-a-disaster-1.99558
    https://www.cs.uaf.edu/2013/fall/cs471/Pres/DoD.pdf
  The list never ends….

## Slide 10: Worst Practices in Software Engineering
The disastrous launch of HealthCare.gov can be attributed to a multitude of flaws in the project's execution.
From the outset, the endeavor was plagued by an excessive level of complexity, involving three major contracts with distinct contractors, deliverables, and infrastructure components.
This hyper-complex structure, coupled with a reliance on external data sources beyond the project's control, virtually ensured that the website would face significant challenges.

## Slide 11: Worst Practices in Software Engineering
Compounding the inherent complexity was the project's dependency on Experian, a third-party data provider. With no ability to verify or enhance the quality of Experian's data, the system struggled to handle exceptions and inconsistencies, leading to numerous issues and errors.
These fundamental missteps, exacerbated by the politically charged atmosphere surrounding the Affordable Care Act, ultimately culminated in the website's delayed and troubled launch.

## Slide 12: Five key things for project management
In-house vs. Outsourcing: Determine whether to utilize internal resources or to outsource the project.
Vendor Selection and Management: Adhere to best practices in selecting the most suitable vendor for your needs, and maintain effective management of the vendor relationship throughout the project.
Project Leadership: Assign a single individual to oversee the project, granting them the authority to make final decisions.
Transparency and Testing: Address issues promptly and maintain transparency about project progress. Rigorously test the website throughout the development process.
Preparedness: Anticipate both potential success and failure. Establish clear guidelines to manage and mitigate any possible failures.

## Slide 13: System security issues
CMS officials did not conduct a comprehensive end-to-end security test of the site prior to its launch; only individual components were tested.
To date, attention has primarily been directed towards performance and reliability issues, with limited insight into the efforts made to ensure system security.
Given the vast amounts of sensitive data, numerous data sources, and involvement of third-party contractors, significant security breaches on the Obamacare website appear to be an eventuality.

## Slide 14: Conclusion from the GAO report
CMS program and contracting staff made several planning decisions and trade-offs intended to expedite the timeline but that introduced substantial risks.
As performance issues with the FFM contractor emerged late in the development process, CMS was frequently confronted with the dilemma of either holding the contractor accountable for poor performance or focusing entirely on meeting the October deadline.
Simultaneously, CMS continues to face challenges in defining requirements and controlling costs to finalize the development of the financial management module in the FFM.
  Source: http://www.gao.gov/assets/670/665179.pdf

## Slide 15: Discussion Questions
How do the planning decisions and trade-offs made by CMS program and contracting staff reflect the balance between meeting deadlines and managing risks?
Notes: Discuss how CMS staff prioritized time savings over other project aspects, and the implications of such decisions. Reflect on whether a different balance between expediting timelines and risk management might have resulted in a more successful launch. Consider the roles of accountability and oversight in this context, and explore how these aspects can be effectively managed in large-scale IT projects.

## Slide 16: Discussion Questions
Why is end-to-end testing crucial for complex systems, and what lessons can be learned from CMS’s approach of only testing individual components?
Notes: Analyze the decision to forego comprehensive end-to-end testing in favor of testing individual components. Discuss the potential risks this posed to the overall system security and reliability. Consider how a lack of integrated testing might affect other large-scale projects, and propose strategies to ensure that comprehensive testing is incorporated into future project plans.

## Slide 17: Discussion Questions
Given the involvement of multiple data sources and third-party contractors, how should organizations prepare for potential security breaches in complex systems like the Obamacare website?
Notes: Evaluate the statement that significant security breaches on the Obamacare website appear to be inevitable due to the vast amounts of sensitive data and numerous data sources. Discuss the importance of proactive security measures and preparedness strategies in managing such complex systems. Consider the role of continuous monitoring, vendor management, and incident response plans in mitigating security risks.

## Slide 18: Resources
  https://en.wikipedia.org/wiki/HealthCare.gov
  http://www.chambers.com.au/public_resources/case_study/obamacare/saving-obamacare-case-study.pdf
  http://www.gao.gov/assets/670/665179.pdf
  https://hackernoon.com/small-is-beautiful-the-launch-failure-of-healthcare-gov-5e60f20eb967